## Assumptions
The task breakdown makes the following assumptions:
Development and testing time is excluded, although time spent upfront on designing the test / acceptance process is included
Formal user training is excluded, although time spent assisting and educating users as part of migration is included
It is assumed that no exhaustive bottom up analysis will take place; a scope will be defined based on key reports and ad-hoc use cases and this scope will cover the most important fields. Other fields may need to be brought into SolarBI later.
Migration of business reports and Access DBs includes a parallel run period. No distinction is made between ad-hoc and regular queries (because these seem to be mixed together in the existing assets), so the parallel run includes both producing and comparing regular reports, and testing ad-hoc use cases.
IRB acceptance / testing is not budgeted as it's not clear whether how this will interact with the Solar programme, but there may well be days required from IRB staff to validate and accept the historical data once migrated
The breakdown into 'Senior' and 'analyst' is indicative -- in practise some tasks marked 'senior' may be carried out by Solar programme management, for example
Migration estimates include time required from Solar staff but not time spent on acceptance/testing by business staff
With the exception of historical data migration, there is flexibility throughout this plan based on how much work to do upfront, and how much to do reactively in response to problems and requests that arise. The sensible ratio may be somewhere around 80% upfront coverage, and 20% work done reactively after the business migration begins; the tradeoff is between minimizing total expense upfront, versus minimizing issues encountered by business.
Executive summary
The estimate comes to about 5 man-months.
It is important to note that there are some factors that may cause a low velocity: the remaining uncertainties and assumptions, the need to co-ordinate with Spain based teams, and in particular the need to change business skills sets and workflows.

## Task breakdown
Task | Subtask | Senior resource days | Analyst days | Deliverables | Dependencies | Notes
Inception | Project inception | 3 | 5 | Knowledge base, set of access DBs and ficres/mainframe files, technical points of contact, project plan
Map remaining fields | Define set of reports / access DBs in scope | 2 |  | A set of Access DBs which will form the scope for further analysis |  | Assuming about 16 access DBs form the core set
| Compile list of fields and diff with SolarBI dictionary | 1 | 1 | A list of fields found in the in-scope DBs, but not in SolarBI | Requires understanding of SCUK terms in some cases
| Check whether missing fields are required | 1 |  | A revised list of fields to be mapped.
| Map to mainframe or FICRES |  | 10 | Mappings similar to those produced for SAS Upgrade, covering the field list | Requires analysis of sagent/COD code
Validate assumptions | Check effect of joining with GIB accounts list |  | 1 | Confirmation of the role (if any) GIB plays in data quality | Need ability to run Access | Just a matter of running queries with/without the join. MAY uncover quality features that need to be duplicated in SolarBI
| Check rate/nature of historical amendments | 1 |  | Confirmation that reading historical data from the mainframe will *not* result in breaks caused by inconsistent amendment of data between Oracle and mainframe | MF access and MF team resource | Could start by comparing SolarBI historical data to MF
| Check for additional fields required by ad-hoc use cases | 1 | 1 | List of additional in-scope fields identified by discussion with business rather than by analysis of EUDAs. |  | Best approach may be to present a list of in-scope fields and challenge business representatives to identify fields recently used but not in the list.
| Verify Retail Risk data needs | 2 | 3 | Additional requirements from Retail Risk. If these are onerous, there may be an impact on overall delivery effort. | RR business stakeholders, Sagent access | RR claim that they would need all MIPROD columns; a compromise needs to be found here. Fully replicating all of MIPROD would involve analyzing about 800 columns; however, many of these are blank. The total set of Sagent logic forms a fixed scope for the work. Fully replicating all of MIPROD might thus require an additional 20-25 days of analysis.
| Check how daily SAS file is produced and identify any logic needed in SolarBI |  | 2 | Additional requirements from Retail Risk. If these are onerous, there may be an impact on overall delivery effort. | Sagent access
Plan historical data migration | Check consistency of historical data | 1 | 2 | Report on the variation (if any) in file formats on the mainframe from month to month. | Solar access tool would be very useful. Also requires MF access and MF team resource.
| Map fields to SolarBI fields |  | 5 | Mappings relating each historical data field to SolarBI. | Requires understanding of SCUK terms in some cases. Requires list of in-scope fields to have been confirmed. | This probably requires documenting transformation as well as directly mapping fields
| Plan amendment/refresh process if necessary | 1 | 1 | Requirements for a process to be implemented in SolarBI to ensure that historical data in SolarBI remains synchronized with the mainframe
| Coerce historical data to a consistent format |  | 5 | A process for converting any historical data month into a consistent format reflecting the most recent mainframe records. | Depends on the output of 'check consistency of historical data' | This involves coming up with rules that transform any historical data month into a 'modern' month
| Draw up test plan | 1 | 1 | Set of test cases, input data and expected results. This is in addition to any testing required within the IRB programme.
Migrate users | Evaluate user needs and socialize new environments (SAS/BO) with users | 5 |  | Set of policies for migrating each user group specifying licenses, training and time required, agreed with each user group
| Plan migrations, identify points of contact, define schedule for each team | 5 |  | Point of contact and project plan for each user group
| Migrate 1 Customer Services DB |  | 5 | (Delivered jointly with business) Migrated DB and parallel run results
| Migrate 2 manufacturer extracts |  | 8 | Manufacturer extracts reimplemented in SolarBI | Test and parallel run with Christian
| Migrate 6 New Business DBs |  | 12 | (Delivered jointly with business) Migrated DB and parallel run results | Need Lindsay or other point of contact
| Migrate 12 Finance DBs |  | 20 | (Delivered jointly with business) Migrated DB and parallel run results | Need Chloe or other point of contact | Assumption is that the unexamined DBs are broadly similar to the ones already examined, and that no exhaustive like for like replacement of queries is required.
| Migrate RM reports | 2 | 10 | (Delivered jointly with business) Migrated DB and parallel run results | Need time with Alan Harding | This is difficult to estimate upfront, a conversation with Alan is required to understand how much reporting is really 'live'
| Total days per role: | 23 | 87
| Total days: | 110